A Collaborative Initiative of the Association of Nigerian Authors (ANA), Kwara State Chapter and Ilorin Innovation Hub

## Background and Rationale

Nigeria possesses a vibrant tradition of storytelling, journalism, and literary creativity. However, the rapid transformation of the global media landscape through digital technology and artificial intelligence has created new demands on writers, journalists, and cultural producers. Many emerging creatives especially in secondary cities such as Ilorin often lack structured access to digital tools, mentorship, and professional networks that can help them adapt to these evolving forms of storytelling.

At the same time, there is a growing need to preserve Nigeria’s cultural narratives while presenting them through modern multimedia platforms. Local histories, indigenous languages, oral traditions, and community experiences risk being underrepresented in digital spaces if young creators are not equipped with the necessary skills to document and share them responsibly.

The Digital Storytelling, Journalism, and Creative Innovation Initiative (DSJCII) emerges from this need to bridge the gap between traditional literary practice and contemporary digital innovation. By promotimg collaboration between literary institutions and technology-driven innovation ecosystems, the initiative seeks to build a new generation of storytellers who are both culturally grounded and digitally skilled. The partnership with the Association of Nigerian Authors (Kwara State Chapter) headed by Dr. Mohammed El-Nasir Al-Amin is crucial because the organization has historically served as a leading platform for nurturing literary talent, mentoring writers, and promoting Nigerian literature. Their experience in literary development and cultural advocacy ensures that the initiative remains rooted in strong storytelling traditions and ethical narrative practices.

Equally important is the collaboration with the Ilorin Innovation Hub, an initiative of the Kwara State Government aimed at positioning the state as a centre for technological advancement and youth-driven innovation. The Innovation Hub provides access to digital infrastructure, technical expertise, and a vibrant ecosystem of innovators and entrepreneurs. This partnership enables the integration of technology, artificial intelligence, and digital media tools into storytelling and journalism training.

Bringing these institutions together creates a powerful synergy: literary excellence from the Association of Nigerian Authors combined with technological innovation from the Ilorin Innovation Hub. This collaboration aligns with broader efforts by the Kwara State Government to support youth empowerment, digital skills development, and creative industries as drivers of economic growth. Ultimately, the initiative seeks to position Ilorin not only as a city of rich cultural heritage but also as a growing centre for digital storytelling, media innovation, and creative entrepreneurship in Nigeria.

## Project Aim

To promote collaboration between writers, journalists, digital creators, and technology innovators in order to enhance creative storytelling, digital journalism, and cultural preservation using innovative technological tools.

## Objectives

- Train emerging writers and journalists in digital storytelling and multimedia reporting.

- Introduce participants to AI-assisted creative and journalistic tools.

- Support digital publishing and creative entrepreneurship.

- Preserve indigenous narratives and oral histories through digital documentation.

- Promote collaboration between the literary, media, and technology sectors.

- Strengthen youth engagement in Nigeria’s creative economy.

## Programme Components

1. AI Writing and Media Lab

- Training on AI-assisted storytelling, automated transcription, editing, and ethical use of AI.

- Participants learn to enhance creativity with technology while maintaining authenticity and integrity.

2. Digital Publishing and Media Incubator

- Mentorship for writers, journalists, and creatives to produce ebooks, digital magazines, podcasts, and multimedia journalism projects.

- Guidance on market-ready content, monetization, and digital distribution.

3. Literary and Media Hackathon

- Collaborative event bringing together writers, journalists, developers, designers, and digital artists.

- Teams will create interactive storytelling platforms, digital journalism tools, and multimedia experiences.

- Winning projects receive mentorship and incubation support.

4. Youth Creative Writing and Journalism Bootcamp

- Week-long intensive training for secondary school and university students, focusing on:

  - Creative writing

  - News and feature reporting

  - Spoken word and literary performance

  - Media ethics and responsible journalism

5. Ilorin Cultural Story and Media Archive

- Digital documentation of oral histories, folklore, myths, and community narratives.

- Creates a long-term repository of Ilorin’s cultural heritage.

6. Annual Digital Literary Festival

- Public festival showcasing:

  - Literary readings and poetry performances

  - Digital storytelling projects

  - Journalism panels and media conversations

  - Technology demonstrations

## Implementation Timeline (12 Months)

- Months 1–2: Project planning, partnership agreements, publicity, participant recruitment

- Months 3–4: AI Writing and Media Lab training sessions

- Months 5–6: Digital Publishing and Media Incubator mentorship

- Month 7: Youth Creative Writing and Journalism Bootcamp

- Months 8–9: Literary and Media Hackathon, mentorship for winning teams

- Months 10–11: Ilorin Cultural Story Archive development

- Month 12: Digital Literature and Journalism Festival, project evaluation, and final reporting

## Monitoring and Evaluation Framework

Indicators:

- Number of participants trained in writing, journalism, and digital storytelling

- Number of digital publications and media projects produced

- Youth participation from schools and universities

- Partnerships established with cultural and media institutions

- Public engagement and media coverage

Monitoring Methods:

- Registration and attendance tracking

- Pre-training and post-training assessments

- Participant surveys and feedback

- Documentation of creative outputs

- Quarterly progress reports

Evaluation:

- Independent evaluation to assess effectiveness, sustainability, and long-term impact on participants and the creative ecosystem.

## Potential Sponsors and Partners

- Kwara State Government

- British Council Nigeria

- Ford Foundation

- Nigeria LNG (NLNG)

- MacArthur Foundation

- Goethe-Institut Nigeria

- MTN Foundation

- Bank of Industry – Creative Sector Fund

- Federal Ministry of Arts, Culture and Creative Economy

- Universities, media organisations, and private sector technology partners

## Estimated Project Budget (₦52,000,000)

| Budget Item | Estimated Cost (₦) |
| --- | --- |
| Project management and coordination | 9,500,000 |
| AI Writing & Media Lab | 5,500,000 |
| Digital Publishing & Media Incubator | 6,000,000 |
| Youth Writing & Journalism Bootcamp | 3,000,000 |
| Literary & Media Hackathon | 3,500,000 |
| Ilorin Cultural Story Archive | 2,500,000 |
| Digital Literature & Journalism Festival | 15,000,000 |
| Media publicity and communications | 2,500,000 |
| Monitoring & evaluation | 1,500,000 |
| Contingency | 2,500,000 |
| Total | 52,000,000 |

## Conclusion

The Digital Storytelling, Journalism, and Creative Innovation Initiative provides a strategic platform to integrate literature, journalism, and technology in Nigeria’s creative ecosystem. By empowering emerging writers, journalists, and digital creators, the project will preserve cultural heritage, enhance youth skills, and support creative entrepreneurship. With the support of public institutions, cultural organizations, and private sector partners, this initiative will position Kwara state as a leading hub for digital storytelling, journalism, and media innovation in Nigeria.