# IIH Programs Governance and KPI Framework

## Overview

This document defines governance, accountability, and KPI measurement structure for IIH programs across the CcHUB and Future Africa delivery streams. It consolidates stream-level governance with performance management templates for monthly and quarterly decision-making.

## Governance Structure

### Pre-Incubation, Incubation & Ecosystem Development (CcHUB) Governance

Strategic Steering Committee: provides strategic direction, approves priorities, and resolves escalated blockers.

Program Management Office (PMO): coordinates delivery plans, dependencies, reporting cadence, and portfolio tracking.

Operational Technical Group (OTG): manages execution readiness, operational support, and technical delivery controls.

Reporting & Accountability: monthly reporting to leadership with owner-based accountability and corrective action tracking.

### Acceleration, Corporate Innovation & Technical Training (Future Africa) Governance

Strategic Steering Committee: sets direction and validates performance against strategic outcomes.

Program Management Office (PMO): manages workplan execution, cross-team dependencies, and reporting quality.

Operational Technical Group (OTG): ensures operational execution, training readiness, and quality assurance.

Reporting & Accountability: monthly and quarterly reporting with clear ownership and escalation triggers.

## Communication Protocol

All workstreams report against agreed templates, timelines, and accountable owners. Critical variances are escalated according to defined thresholds and action windows.

## Performance Indicators

### CcHUB: Incubation, Pre-Incubation & Ecosystem Development

| Workstream | KPI | Definition | Target | Frequency |
| --- | --- | --- | --- | --- |
| Incubation | Incubation Conversion Rate | Qualified pipeline converted into incubation | >=30% | Monthly |
| Incubation | Startup Support Effectiveness | Incubated startups meeting milestone plans | >=80% | Quarterly |
| Pre-Incubation | Program Completion Rate | Participants completing pre-incubation cycle | >=85% | Monthly |
| Ecosystem | Partner Retention Rate | Active partners retained vs prior period | >=80% | Quarterly |
| Ecosystem | Community Engagement Growth | Growth in qualified ecosystem participation | >=15% YoY | Quarterly |

### Acceleration, Corporate Innovation & Technical Training (Future Africa)

| Workstream | KPI | Definition | Target | Frequency |
| --- | --- | --- | --- | --- |
| Acceleration | Cohort Delivery Adherence | Planned milestones delivered on schedule | >=90% | Monthly |
| Corporate Innovation | Enterprise Engagement Success | Corporate projects achieving agreed outputs | >=85% | Quarterly |
| Technical Training | Training Completion Rate | Learners completing assigned track | >=85% | Monthly |
| Technical Training | Placement/Outcome Rate | Graduates placed in jobs/projects/ventures | >=40% | Quarterly |
| Technical Training | Instruction Quality Score | Average participant quality score | >=4.2/5 | Monthly |

## KPI Dictionary Annex

| KPI | Definition | Formula | Data Source | Owner | Frequency | Target | Variance Threshold |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Program Completion Rate | Share of enrolled participants who complete program | Completed / Enrolled | Program tracker / LMS | Program Manager | Monthly | >=85% | -10% |
| Incubation Conversion Rate | Share of qualified pipeline converted into incubation | Incubated / Qualified pipeline | Incubation tracker | Program Manager | Monthly | >=30% | -5% |
| Training Placement Rate | Share of graduates with validated outcomes | Placed / Graduated | Placement tracker | Technical Training Lead | Quarterly | >=40% | -8% |
| Partner Retention Rate | Share of active partners retained | Retained / Prior active partners | Partnership register | Ecosystem Lead | Quarterly | >=80% | -10% |
| Cost per Participant | Average unit cost per participant | Program cost / Participants | Finance + Program reports | Finance Associate | Monthly | Within budget | +10% |

## Governance RACI Annex

| Function | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| KPI definition and revision | Program Manager | Director of Programs | Finance, M&E | MD, Steering Committee |
| Monthly KPI reporting | Program Manager | Director of Programs | Finance Associate | MD, PMO |
| Quarterly performance review | Director of Programs | MD | Ops, Finance, PMO | Program Leads |
| Corrective action tracking | PMO/Project Manager | Director of Programs | Function Owners | MD |

## Escalation Matrix

| Trigger | Escalation Level | Action Window | Required Action |
| --- | --- | --- | --- |
| KPI below threshold (1 cycle) | Director of Programs | 5 working days | Root-cause and recovery plan |
| KPI below threshold (2 cycles) | MD / Steering Committee | 10 working days | Intervention plan and resource decision |
| Critical delivery slippage (>15%) | MD | Immediate | Re-baseline timeline and accountability reset |

## Monthly Dashboard Template (1-Page)

| Workstream | KPI | Target | Actual | Variance | Root Cause | Corrective Action / Owner / Due Date |
| --- | --- | --- | --- | --- | --- | --- |
| Incubation |  |  |  |  |  |  |
| Ecosystem Development |  |  |  |  |  |  |
| Acceleration & Corporate Innovation |  |  |  |  |  |  |
| Technical Training |  |  |  |  |  |  |