December 21, 2020

Ref: IIH/MD/2020/12/013

His Excellency,
The Executive Governor of Kwara State,
Government House,
Ahmadu Bello Way,
GRA, Ilorin, Kwara State.

Your Excellency Sir,

REQUEST FOR APPROVAL OF Q1-Q2 2021 ILORIN INNOVATION HUB ACTIVITY PLAN

As the year comes to a close, and In preparation for the new year, we are putting plans in place for the build-up to the launch of our Innovation Hub. This will involve several programs within the Innovation Hub and external partnerships.

As the construction of the building is still in the early stages, it would be great for there to already be several activities that have come to fruition by the time the building is completed.

Below is a tentative list of activities for next year, but not limited to this list.

| SN | Activity | Projected Timeframe |
| --- | --- | --- |
| 1 | Launch Ilorin Startup Accelerator Program – ISAP (call for entries) | December 2020 |
| 2 | Joining Afrilabs – Africa’s largest network of Innovation Hubs | January 2021 |
| 3 | Signing of MoU with University of Ilorin | January 2021 |
| 4 | Signing of MoU with other Strategic Partners | January - February 2021 |
| 5 | Launch Tech Skills Bootcamp | January 2021 |
| 6 | Launch Kwara State ICT Advisory Group | January 2021 |
| 7 | Launch KwaraJobs.com | February 2021 |
| 8 | First Cohort of ISAP Launch Startup Academy Program | February 2021 – May 2021 |
| 9 | Educational Technology Implementation Plan Launch | February 2021 |
| 10 | Constitution of the Ilorin Angel Investor Network | March 2021 |
| 12 | Kwara State ICT Framework Launch | April 2021 |
| 11 | Kwara Innovation Summit ISAP First Cohort Demo Day | June 2021 |

So as to properly execute the activities listed above, we would need to conclude on the process of company registration structure changes for Ilorin Innovation Hub Ltd, as has been initiated with Harmony Holdings Ltd.

Yours truly,

Temi Kolawole
MD Ilorin Innovation Hub