Dec 11, 2023

Addressed to Consultant

Dear Sir,

INNOVATION HUB PARTNERSHIP: NEW PROJECT SCOPE AND DELIVERABLES

Due to the new partnership between the Kwara State Government and IHS Towers to participate in the delivery of the Project by way of providing financial,

technical and organizational support to the build, operations, maintenance and management of the Kwara ICT Innovation Hub (Ilorin Innovation Hub) and sequel to our meeting on the 30th of November 2023 where all stakeholders were introduced to the new partners, we write to communicate the changes being made to align with the new plan and strategy for the project’s success and sustainability.

| SN | AREA | SUGGESTED USE/CHANGE | COMMENTS | RESPONSIBLE |
| --- | --- | --- | --- | --- |
|  | Changes Within Existing Project Scope |  |  |  |
| 1 | Reception | Remove Large Square Storage Block | It serves no real purpose and takes up valuable space. Proposal for reception to be along large wall to the left | Main Contractor |
| 2 | Ground Floor Meeting Room | DB Box has been placed here, and is not convenient. Meeting room needs to be moved. | Space Finish and Contractor to discuss this and propose solution | Main Contractor Fit-Out Contractor |
| 3 | Outside (Front) | More Trees/Green area | Large tree cut down by contractor was not authorised | Main Contractor |
| 4 | Outside (Back) | Increase parking space from 30 to 50. Consultant asked to redesign landscape plan |  | Main Contractor |
| 5 | Side Outdoor Sitting | Move soak away farther from building to allow roofed area to be used for outdoor sitting area |  | Main Contractor |
| 6 | Roof/Drainage |  | Needs to be redone, retrofitting suggestion already discussed with IHS Team | Main Contractor |
| 7 | Generator House | Should be moved to the front of building beside transformer | To reduce the cost of wiring (underground armored cables) and to keep power infrastructure together. Power in front, water and tanks at the back | Main Contractor |
| 8 | Overall Drainage |  | This needs to be double checked from the roof to the gutters and outlet behind building | Main Contractor |
| 6 | Green Mold on back Wall |  | This needs to be looked into | Main Contractor |
|  | Changes Outside Existing Project Scope |  |  |  |
| 9 | Restaurant | Open workspace & VIP Lounge | The proposed restaurant area is too large, and is valuable workspace. We want people to be seen working immediately you step into the building. | IHS Fit-Out Contractor |
| 10 | Kitchen | Cafeteria (Eating Room) | There's no need for food to be cooked within the premises, since the restaurant is now additional workspace. The cafeteria will be a place with a microwave and refrigerator for members to warm food and sit to eat | IHS Fit-Out Contractor |
| 11 | Kitchen Store | Additional toilets | The existing toilets are not adequate for the building, especially during large events. This space is close to existing toilets | IHS Main Contractor |
| 12 | Multi-Purpose Hall | Moveable partitioning into two or three sections |  | IHS Fit-Out Contractor |
| 13 | Auditorium/Pitch Room |  | Wait for Space Finish's Suggestions | IHS Fit-Out Contractor |
| 14 | Coffee Lounge | Converted into workspace, coffee stand to be placed against wall |  | IHS Fit-Out Contractor |
| 15 | Space beside Coffee Lounge | Extended workspace area |  | IHS Fit-Out Contractor |
| 16 | Open Space Adjacent to Ground Floor offices | Create Space for Additional toilets |  | IHS |
| 17 | First Floor Walkway | To be used as additional workspace |  | IHS Fit-Out Contractor |
| 18 | First Floor Corner Space/Relaxation area | Kept as workspace, games like table tennis, snooker to be scattered around building |  | IHS Fit-Out Contractor |
| 19 | Elevators | 1 in front, 1 at the back |  | IHS |
| 20 | Solar Power Grid |  | Need to locate battery room | IHS |
| 21 | Central Air Conditioning System |  | Previous AC Costs to be removed from Main Contract BOQ | IHS |
| 22 | Additional Door at Back | The need for one more entry/exit door was raised |  | IHS Main Contractor |

The changes outside of the existing project scope will be handled by IHS Towers, while those within are to be borne within the scope covered by the Kwara State Government. We would ask the responsible parties to quickly prepare/adjust their costing and Project plans to reflect the new changes and commence work immediately. These new documents should be submitted by December 18, 2023.