## Ilorin Innovation Hub Facility Operations Upgrade Proposal

### For the Learn2Earn Program

### 1. Background

The Ilorin Innovation Hub (IIH) is set to host the Learn2Earn Program, a skill-building and income-generating initiative designed to empower young learners through digital, creative, and technical education. To ensure a smooth experience for participants and facilitators, the Hub’s facility operations need to be enhanced to support extended hours, reliable and faster connectivity, and sustained comfort across all service points.

### 2. Objective

This proposal outlines the required upgrades to IIH’s facility operations to accommodate the Learn2Earn Program efficiently and safely. It covers staffing, furniture, infrastructure, and operational adjustments to ensure an optimal learning environment.

### 3. Scope of Work

#### 3.1 Staffing

Facility Team

- Add two weekend facility officers to handle maintenance and supervise cleaning and security on Saturdays and Sundays.

- Implement a rotational schedule within department to balance workload and maintain cleanliness standards.

IT Support

- Engage one IT support staff for weekend sessions.

- Provide training in troubleshooting participant laptops, managing shared systems, and ensuring stable connectivity.

- Assign a Technical Coordinator to oversee all Learn2Earn-related IT needs.

Front Desk & Administration

- Extend front desk coverage to weekends (Saturday–Sunday, 9 AM–6 PM).

- Introduce participant access identification (tags, passes, or digital QR codes).

- Integrate Learn2Earn attendance and access tracking into the front desk workflow.

#### 3.2 Furniture

Learning Areas

- Acquire  additional ergonomic desks and chairs suited for long-duration learning sessions in Workspace 2 (upstairs).

- Adopt flexible layouts to accommodate both group and individual learning setups.

- Explore additional partitioning to create additional secure learning and workspace areas upstairs.

- 4 more long workspace desks with power outlets and connections, and 50 new workspace chairs.

Lounge & Recreation Zones

- Ensure clear zoning between learning and relaxation areas (done).

- Introduce acoustic or soft dividers to minimize noise interference.

#### 3.3 Infrastructure

Connectivity

- Upgrade internet bandwidth from 45 MBPS to 155MBPS STM1 to sustain 7-day usage and high weekend traffic.

- Establish a redundant ISP link to reduce downtime risk.

- Install Wi-Fi repeaters in classrooms and public areas for consistent coverage.

Hardware and Software

- Provide PCs and for program participants.

- Maintain & manage external rented computers

- Ensure all systems run up-to-date operating systems and essential productivity tools (e.g., Virtualized Ubuntu).

- Install smart TVs or projectors in classrooms for instructional display.

#### 3.4 Operational Hours and Access

- Extend IIH operation to 7 days a week.

  - Monday–Friday: Normal public access 9am-6pm.

  - Saturday–Sunday: Access limited to Learn2Earn participants and scheduled events.

- Update digital platforms and staff schedules to reflect the new hours.

- Implement a controlled entry system (access cards, tags, or QR codes) for all workspace participants.

#### 3.5 Utilities and Maintenance

- Explore increasing power backup capacity to support weekend operations.

- Adjust air conditioning and electrical maintenance schedules for continuous service.

- Expand cleaning services to cover two additional days, including Sunday operations and midday weekend rounds, with a weekly deep-cleaning on Sunday evenings or Monday mornings.

#### 3.6 Safety and Compliance

- Ensure all active zones have first aid kits and functioning fire extinguishers.

- Conduct monthly facility safety checks including electrical systems, emergency exits, and signage.

#### 3.7 Communication and Coordination

- Update the internal operations handbook to reflect weekend roles and procedures.

- Create a dedicated communication channel (WhatsApp) for Learn2Earn operations staff.

- Design and circulate a standard incident reporting form for weekend activities.

### 4. Existing Amenities (Already Met)

- Food Service: The IIH Cafeteria is fully operational, serving breakfast, lunch daily – will explore extending to 7-day service.

- Recreation: Darts, board games, card games, and foosball are available. Table tennis and air hockey will be added shortly.

### 5. Implementation Plan

- Conduct an on-site audit to assess existing furniture, power points, and connectivity coverage.

- Develop cost estimates and a budget breakdown for staffing, equipment, and utilities.

- Initiate a one-month pilot weekend operation for Learn2Earn participants.

- Review performance and feedback, then finalize full implementation.

### 6. Budget Overview

| ### Category | ### Item / Description | ### Qty / Units | ### Estimated Unit Cost (₦) | ### Estimated Total (₦) | ### Remarks / Notes |
| --- | --- | --- | --- | --- | --- |
| ### 1. Staffing | ### Additional Facility Support Officer | ### 2 staff | ### 252,000 | ### 504,000 | ### Handling facility maintenance, supervising cleaning, security |
|  | ### Additional Front Desk Officer | ### 1 staff | ### 252,000 | ### 252,000 | ### Participant attendance and access control |
|  | ### Additional IT Support | ### 1 staff | ### 252,000 | ### 252,000.00 | ### Troubleshooting, connectivity, support |
| ### Subtotal: Staffing |  |  |  | ### ₦1,008,000 | ### For 2/12 months left in 2025 |
| ### 2. Furniture | ### Ergonomic Chairs | ### 50 | ### 90,000 | ### 4,500,000 | ### In Workspace 2 |
|  | ### Long Workstation Desks | ### 4 | ### 4,000,000 | ### 16,000,000 | ### Including, power strips |
| ### Subtotal: Furniture |  |  |  | ### ₦20,500,000 |  |
| ### 3. Infrastructure – Connectivity | ### Internet Bandwidth Upgrade | ### 1 plan | ### 1,125,971.33 | ### 1,125,971.33 | ### Difference in cost to upgrade speed |
|  | ### Wi-Fi Repeaters | ### 4 | ### 50,000 | ### 200,000 | ### For full coverage in classrooms |
| ### Subtotal: Connectivity |  |  |  | ### ₦1,906,594.7 |  |
| ### 4. Utilities & Maintenance | ### Additional Cleaners (shift) | ### 2 | ### 100,000 | ### 200,000 | ### New cleaners engaged to complement existing |
|  | ### Cleaning Supplies & Consumables | ### 1 | ### 100,000 | ### 100,000 |  |
| ### Subtotal: Utilities & Maintenance |  |  |  | ### ₦300,000 |  |
| ### Contingency (5%) |  |  |  | ### 1,185,729.74 |  |
| ### Grand Total (Estimated) |  |  |  | ### ₦24,900,324.40 |  |

### 7. Monitoring and Evaluation

- Weekly feedback from program facilitators and operations staff.

- Monthly review of attendance, facility usage, and utility consumption.

- Quarterly assessment of infrastructure performance and participant satisfaction.

### 8. Conclusion

Upgrading the Ilorin Innovation Hub’s facility operations to a full 7-day model will enhance its ability to host intensive programs like Learn2Earn. This plan provides a roadmap for achieving comfort, reliability, and sustainability across all operational areas, aligning with the Hub’s broader mission of empowering innovation and skill development in Kwara State.

The total cost to achieve this is N24,900,324.40.